## Strip-Out Schedule
LEGACY BUSINESS ENGINEERS LTD
STRIP-OUT SCHEDULE
Project: [NAME] ¦ Rev: [A] ¦ Date: [DD/MM/YYYY] ¦ Survey: [DD/MM/YYYY]
Ref | System | Item Description | Location | Floor | Qty | Unit | Contains Refrigerant | Contains Asbestos | BC Notification Required | Isolation Required | Isolation Type | Disposal Method | Contractor | Access Constraints | Duration | Sequence/Dependency | Status | Notes
ELECTRICAL STRIP-OUT
SO-E01 | Electrical | Existing DBs |  |  |  | Nr | N | CHECK | Yes if FA zone affected | Yes — isolate at MSB | Electrical | WEEE | Elec |  |  | Before ceiling strip
SO-E02 | Electrical | Existing lighting |  |  |  | Nr | N | CHECK pre-2000 | No | Yes — isolate at DB | Electrical | WEEE | Elec |  |  | After ceiling access
SO-E03 | Electrical | Existing containment |  |  |  | m | N | CHECK | No | Yes | Electrical | Metal recycle | Elec |  |  | After cables removed
SO-E04 | Electrical | Fire alarm devices |  |  |  | Nr | N | N | Yes — notify fire officer + BC | Yes — isolate zone | Electrical | WEEE | FA specialist |  |  | Coord with fire officer
SO-E05 | Electrical | Emergency lighting |  |  |  | Nr | N | N | Yes if means of escape | Yes — isolate at DB | Electrical | WEEE + battery | Elec |  |  | Temporary EL during works
MECHANICAL STRIP-OUT
SO-M01 | Mechanical | Existing AHU |  |  |  | Nr | N | CHECK filters/lagging | No | Yes — elec + hydraulic | Both | Plant disposal | Mech | Crane/forklift |  | Before ductwork strip
SO-M02 | Mechanical | Existing boiler/chiller |  |  |  | Nr | CHECK F-gas | CHECK | No | Yes — elec + gas/hydraulic | Both | F-gas recovery first | Mech | Plant room |  | F-gas cert before removal
SO-M03 | Mechanical | Existing ductwork |  |  |  | m² | N | CHECK lagging pre-2000 | No | N/A | N/A | Metal recycle | Mech | Ceiling access |  | After AHU isolated
SO-M04 | Mechanical | Existing pipework |  |  |  | m | N | CHECK lagging pre-2000 | No | Yes — drain down | Hydraulic | Metal recycle | Mech |  |  | After plant isolated
PLUMBING STRIP-OUT
SO-P01 | Plumbing | Existing sanitary ware |  |  |  | Nr | N | N | No | Yes — water isolation | Hydraulic | Skip | Plumbing |  |  | Before floor works
SO-P02 | Plumbing | Existing pipework |  |  |  | m | N | CHECK lead pre-1970 | No | Yes — water isolation | Hydraulic | Metal recycle | Plumbing |  |  | After sanitary removed
MANDATORY PRE-COMMENCEMENT:
1. Asbestos R&D Survey per S.I. 386/2006 — mandatory before ANY strip-out. Accredited analyst.
2. F-gas recovery per EU 517/2014 before equipment removal. Certificate required.
3. Electrical isolations per IS 10101:2020 §537. Lock-out/tag-out mandatory.
4. Waste transfer notes per Waste Management Act 1996.
5. BC notification where strip-out affects fire detection (IS 3218), emergency lighting (IS 3217), or means of escape.
6. Temporary life safety systems must remain operational where building occupied.
7. CHECK = site survey required to confirm. Do not assume from drawings.